## Sheet1
AWS Projects and Dependencies
Sr.No | Project Name | Task | Dependency | Remark
1 | DGH-NDR | 2 EC2 Instances | Haliburton | Prerit requires clarification regarding these EC2 instances and their use case within the project. Haliburton has not yet provided clarification.Last mail - 10th Feb 2026.
2 | DGH-IMS | SCP Policy Phase 3 | PWC | PWC has not yet provide approval for phase 3 policy.Mailed to customer 2nd Feb-2026
3 | DGH-IMS | IAM User - deletion | DGH-IMS/PWC | Prerit has mailed customer to deleting user and restricting access to user as well.
4 | NATGRID | Solution is being re-checked | AWS | Sanjeev Saini is currently reviewing the solution at his end, as discussed in the last meeting with NATGRID.No-mail is send to customer because it is pending from AWS end.
5 | Billing Customer | 3 Billing Migration Pending | Customer End | >YK – Innosoft: SOR is not matching. >Incresol: The customer did not join the call. >SoftLink Global: No call has been received since the SOF was shared.